## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
2191-swen-261-12-c DawgsAndCats

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | ZH, 10/10/2019 |  |  | Pass | ZH 11-22-2019
As a player I want the UI to send my move to the model so it can be validated | Given a player makes a move on the board, the move should be received by PostValidateMoveRoute and create a move object to be validated |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
As a player, I want simple moves validated so that I can legally move my pieces around | Given a player makes a move with a single piece, when that move is sent to the model, I expect the model to validate a move to see if it is a simple move |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given a player makes a move with a King piece, when that move is sent to the model, I expect the model to validate a move to see if it is a simple move which can go forwards or backwards |  |  | Fail | ZH, 11/6/2019, King can not take pieces backwards currently | Pass | ZH 11-22-2019
As a player, I want to take an opposing players' checker when I make a valid jump move so that the game can be played to have a winner and a loser | Given I make a jump over an opponents piece, when I send my move, I expect that piece to be removed from the board |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
As a player, I want to make single jump moves that are valid so that I can capture the other players' pieces | Given a piece when the piece jumps over another one of their pieces then I expect this to become an invalid piece |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given a piece when the piece jumps over an opponent Player's piece in a continuous diagonal motion, then I expect this to be a valid move, if the space in the same diagonal direction of the opponent's piece is a valid space |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given a piece when I do a valid single jump move then I expect the piece to be in the space two spaces in the diagonal direction of the jump |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given a piece when I do a valid single jump move then I expect that the opponents piece will be removed |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
As a player, I want to make multiple jump moves so that I can capture multiple of the opposing player's pieces in one move | Given a multiple jump move is possible when I make a jump I expect to be able to make another jump |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given a multiple jump move is possible when I make a jump I expect to be forced to make another jump |  |  | Pass | ZH, 11/6/2019 | Pass | ZH 11-22-2019
| Given that the piece is a King, when I go to make jump moves in a multiple jump move sequence, I expect to be able to make none to many jumps backwards |  |  | Fail | ZH, 11/4/2019, King jumping backwards is not working yet | Pass | ZH 11-22-2019
| Given that I perform a multiple jump move, when I perform that move, I expect all opponents' pieces to be removed from the board |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
As a player I want to forfeit so that I can end the match if I need to | Given I am in a match, when I have the page loaded, then I expect to have the option to click the forfeit button |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given I am in a match, when I click the forfeit button, then I expect a confirmation to appear |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given I am in a match, when I confirm a forfeit then I expect the match to end |  |  | Fail | ZH, 11/4/2019, the match does not end for the opponent | Pass | ZH 11-22-2019
| Given I am in a match, when I confirm a forfeit, then I expect to lose the match |  |  | Pass | ZH, 11/4/2019 | Pass | ZH 11-22-2019
| Given I am in a match when my opponent confirms a forfeit, then I expect to win the match |  |  | Fail | ZH, 11/6/2019, opponent does not get a confirmation of the game ending nor is credited for a win | Pass | ZH 11-22-2019
As a spectator I want to join the game session so that I can watch checkers games | Given there is a current game ongoing when I choose a player to watch then I expect to watch the game from that players perspective |  |  |  |  | Pass | ZH 11-23-2019
As a player I want to be able to play an AI so that I can play against the computer | Given I start a game against a CPU, I expect to be able to play a game of checkers the same way as against another player |  |  |  |  | Pass | ZH 11-23-2019
| Given a player is in the lobby when they go to select an opponent then I expect to have the option to play a CPU |  |  |  |  | Pass | ZH 11-23-2019
| Given there is a game between the user and a CPU, I expect the CPU to make moves |  |  |  |  | Pass | ZH 11-23-2019
As a player I want the game to end when one players pieces are all taken so that the game can end | Given that I am in a game with an AI when I win or the AI wins then the proper endgame messages are reported and the game ends |  |  |  |  | Pass | ZH 11-23-2019
As a player, I want to be told the winner of the game so that I can know if I won or lost the game | Given that I am in a game with the AI when I win or lose a game then have some win/loss messages respective to the players in the game |  |  |  |  | Pass | ZH 11-23-2019